## A3 Thinking
Document: | Six Sigma A3 DMAIC template
Tab: | A3 PROJECT MANAGEMENT AND PROBLEM SOLVING THINKING
Source: | Lean Ireland
Contact: | Bernie Rushe, Bernie@LeanIreland.ie, +353 91 870708
1. | WHAT IS AN A3 PROJECT?
An activity that
(a) supports achievement of the continuous improvement objectives
(b) requires > 39 hours dedicated man-hours
(c) has an A3 worksheet
2. | WHERE DO A3 PROJECTS COME FROM?
All functions & all personnel entitled to propose projects
Derived from e.g. continuous improvement objectives or VSM or other business critical source e.g. compliance requirement or safety requirement
All projects pre-screened by snr managers prior to proposal for the master list
The master project list is maintained by the continuous improvement facilitator
3. | A3 OBJECTIVE
To provide a one page (A3, 420mm x 297mm) summary of a programme, project or problem, for the project team & relevant personnel within the organisation
4. | WHY?
Encourages brevity & sharpness of thinking
Tells a logical story on one sheet for all viewers
Provides a common organisation-wide format for all programme, management, project managment & problem solving activities
5. | WHO?
Team leader of the programme or project, or process owner of the area under review
6. | HOW?
Completion of the standard A3 Template. The template usually consistes of 7 to 9 boxes with standard input requirements, that dfollow the six sigma DMAIC path. The template is modified to suit individual projects.
Use photographs, drawings & graphs to tell the story
7. | UPDATE FREQUENCY
The A3 is a living document and is updated as the team moves through the stages of the project
8. | REVIEW FREQUENCY
The A3 document is reviewed by the team and programme or project champion on an as-required basis during the project lifespan. Review frequencies are determined at the start of the project.

## DMAIC steps
Document: | Six Sigma A3 DMAIC template
Tab: | DMAIC CHECKLIST
Source: | Lean Ireland
Contact: | Bernie Rushe, Bernie@LeanIreland.ie, +353 91 870708
Define
1 | Define the problem in terms of impact on the customer & stakeholders
2 | Select the area/process & open A3 (i.e. the project charter)
3 | Form the team (stakeholders)
4 | Elect a leader
5 | Determine the objectives
6 | Draft the project plan (Gantt chart) using DMAIC template
7 | Train the team
8 | Develop draft financial gains and get finance approval
9 | Develop SIPOPC chart & map the process
Measure
9 | Gemba visit/walkthrough: team ‘discovers’ the project area by taking a guided tour and a walk through the current process
10 | Collect relevant data process
11 | Validate measurement system
12 | Draw relevant graphs & charts
Analyse
13 | Root cause process problems with stakeholdres
14 | Identify areas for improvement
15 | Identify portential fixes
16 | Prioritise issues & fixes
17 | Agree selection with stakeholders
Improve
18 | Identify and make ready all tools an equipment for change in advance of the of the event
19 | Draw up timetable of tasks and responsibilities for pilot trials and implementation
20 | Convene team at the area & implement changes
21 | Train personnel in new way of doing things
Control
22 | Standardise new processes, SOPs, visual management & SPC
23 | Confirm the financial gains
24 | Conduct post implementation review - snag list & action items
25 | Present to senior management
26 | Recognise and reward team
27 | Determine next improvement activities for team members

## A3 Project Template
Project No. and Name |  | Team members (name & job role) |  | Team photo | Stakeholders (name & jobrole) | #VALUE!
|  | 1. |  |  | 1.
Team leader (name & role) |  | 2. |  |  | 2.
|  | 3. |  |  | 3.
Team sponsor (name & role) |  | 4. |  |  | 4. | Start date ( dd mth yyyy)
5.
Organisation Strategic Objective |  |  |  |  | 6. | Planned end date ( dd mth yyyy)
Customer satisfaction
Define |  | Measure |  | Analyse | Improve | Control
Planned start date: |  | Planned start date: |  | Planned start date: | Planned start date: | Planned start date:
Planned finish date: |  | Planned finish date: |  | Planned finish date: | Planned finish date: | Planned finish date:
Problem statement
The Goal
Financial Validation |  |  | Total | Lessons Learned & Next Steps
| Actual savings $ |  |  | 1.
2.
| Finance sign off |  |  | 3.
www.LeanIreland.ie, +353 91 870708, info@LeanIreland.ie
Note on B2: use standard project numbering system (e.g. 2011-XX) and simple short name
Note on B8: State which strategic objective or programme to which this project best belongs OR does the project contribute to - safety - compliance - business growth - cost reduction - service quality improvement - product quality improvement
Note on B11: DEFINE PHASE ACTIVITIES 1. Define the problem in terms of impact on the customer & stakeholders 2. Select the area/process & open A3 (i.e. the project charter) in Excel 3. Form the team (stakeholders) 4. Elect a leader 5. Determine the objectives Objective format: Action verb + object of the action + from "current state" + to "future state" by "date" e.g Decrease average manufacturing lead time for product X from 10 days to 2 days by 31 Jaunary 2011" 6. Draft the project plan (Gantt chart) using DMAIC template (template exists in AtTask) 7. Train the team 8. Develop draft financial gains and get finance approval 9. Draft SIPOC and map the process SAMPLE TOOLS: A3 template, surveys & voice of the customer results, problem statement, goals, Gantt chart, Microsoft Project (large projects), SIPOC, swimlane process map, cost benefit projection.
Note on E11: MEASURE PHASE ACTIVITIES 1. Walkthrough: team ‘discovers’ the project area by taking a guided tour and a walk through the current process 2. Collect relevant data on processes 3. Validate the measurement system 4. Select data representation charts & draw them SAMPLE TOOLS: Check sheet, gauge R&R, run chart, control chart, bar chart, histogram, Pareto chart, box plot, PCA
Note on H11: ANALYSE PHASE ACTIVITIES 1. Root cause process problems 2. Identify areas for improvement 3. Prioritise issues 4. Identify and make ready all tools an equipment for change in advance of the of the event SAMPLE TOOLS: 5 whys, cause and effects analysis, PCA, data stratification, scatter diagrams, regression, Pareto charts, FMEA, DOE, hypothesis testing
Note on K11: IMPROVE PHASE ACTIVITIES 1. Draw up timetable of tasks and responsibilities for pilot trials and implementation 2. Convene team at the area, pilot & implement changes 3. Train personnel in new way of doing things 4. Standardise new processes, update procedures, implement visual management SAMPLE TOOLS: Project Gantt chart - tasks and timelines, detailed timetable of events, 5S, layout changes, standard work, SMED, TPM, visual workplace, error proofing, FMEA, DOE
Note on N11: CONTROL PHASE ACTIVITIES 1. Conduct post implementation review - snag list & action items 2. Use control charting to prove results and maintain discipline in th area 3. Confirm the financial gains 4. Present to senior management 5. Recognise and reward the team 6. Determine the next improvement activities for the team SAMPLE TOOLS: voice of the customer, run chart, control chart, histogram, PCA, hypothesis testing, FMEA, costing benefit analysis & signoff
Note on B13: DEFINE: Define phase duration guidelines YB = 1 to 2 weeks GB = 2 to 3 weeks BB = 3 to 6 weeks
Note on E13: MEASURE Duration guidelines YB = 1 to 2 weeks GB = 2 to 3 weeks BB = 2 to 4 weeks
Note on H13: ANALYSE Duration guidelines YB = 1 to 2 weeks GB = 2 to 3 weeks BB = 2 to 4 weeks
Note on K13: IMPROVE Duration guidelines YB = 1 to 2 weeks GB = 2 to 3 weeks BB = 2 to 4 weeks
Note on N13: CONTROL Duration guidelines YB = 4 weeks GB = 10 weeks BB = 10 weeks Thisis highly dependent on the nature of the changes made.
Note on B14: DEFINE: Define phase duration guidelines YB = 1 to 2 weeks GB = 2 to 3 weeks BB = 3 to 6 weeks
Note on F15: Bernie Rushe: It is useful to tabulate the size of the issue ain this esction e.g. 100 - Staff members 74 - mobile phones 16 - With high security clearance the scope of the project may involve only those with high secturity clearance.
Note on B16: Bernie Rushe: What is observed? Whos is involved? What is the impact? Use drama and emotion. Avoid catch-all words such as 'inefficient', describe instead what's going wrong.
Note on B23: Bernie Rushe: To change the object of the action, from a current state performance level (a number!) to a future state preformance level (a number, by a specific due date (per cell O9 above right).
Note on B46: TOOLS: See "cost savings checklist" tab, this file See "Cost incurred" tab, this file
Note on F46: A separate sheet should be supplied with all the cost workings i.e. add a final tab for Cost analysis to this file. The traget for green belt level projects is $30K annualised savings, or better
Note on C49: Signature of finance cost accountant required

## Yellow Belt example
Project No. and Name |  | Team members (name & role) |  | Team photo |  | Stakeholders (name & role)
22-001 Meetings Meetings Meetings |  | 1. | Pavel Waclav (IT specialist) |  |  | 1. | All Acme employees, onsite
Team leader (name & 'phone ext) |  | 2. | Gillian Meade (HR genearlist) |  |  | 2. | Customer awaiting decisions
Bernie Rushe, Accountant |  | 3. | Tom Sawyer (Accountant) |  |  | 3. | Acme board who set strategy
Team sponsor (name &'phone ext) |  | 4 | Sylwie Keane (Regulatory mgr) |  |  |  |  | Planned start date ( dd mth yyyy)
Richard Doyle, Lean Ireland | [7 empty] | 16th January 2023
Organisation Strategic Objective | [7 empty] | Planned end date ( dd mth yyyy)
"Effective processes" - pillar 2 of strategy '23 | [7 empty] | 31st March 2023 (end of improve)
Define |  | Measure |  | Analyse |  | Improve |  | Control
Actual start date: 16Jan23 |  | Actual start date: 23Jan23 |  | Actual start date: 6Feb23 |  | Actual start date: 20Feb23 |  | Actual start date: 1Apr23
Actual finish date: 30Jan23 |  | Actual finish date: 10Jan23 |  | Actual finish date: 16Feb23 |  | Actual finish date: 27Feb23 |  | Planned finish date: 14June23
Problem Definition |  |  |  | A25, A47 & A48 are most popular rooms |  | 1 | IT meeting & budget - PW, 4Mar23
Staff at Acme are receiving meeting invitations in excess of available time. At many meetings there is little structure in terms of agenda, clearly defined roles or meeting minutes. The AV equipment required is not always working or even present, resulting in poor decision making, reschedules and repeated meetings. |  |  |  | - natural light, accommodate 10 people, kept clean, AV works |  | 2 | Audit by BM personnel - BR, 14Mar23
[6 empty] | 3 | Meetings guidelines - GM, 11Mar23*
|  |  |  | 51 meetings observed in 'Measure' |  | 4 | Communication - GM, 31Mar23
[6 empty] | 5 | Training - GM & SK, 21Apr23
[6 empty] | 6 | AV visual guidelines - SK & TS, 7Apr23
[6 empty] | 7 | AV installations - PW & TS, 7Apr23
[6 empty] | 7 | MS Outlook adjustments - SK, 14Apr23
[6 empty] | 8 | Closure of 4 rooms - BR, 14Apr23
The Goals
1 | Improve on-time meeting starts from 15% to 80% by 31Mar23.
2 | Improve meeting room utilization from 52% to 70% by 31Mar23.
Fishbone completed with 20 cross department users & shown below
12 gemba walks completed by the team 4 VOC focus groups consulted (n=100)
Customer feedback
[8 empty] | 1 | “I can’t believe how quickly things have changed. Going to meetings is no longer an ordeal.”
VOC Survey results (102/500 reponses)
1 | Fewer meetings (95) | B15 - access via the PA to the MD only | [5 empty] | 2 | “The last 5 meetings I went to started on time & finished early with solid agreements reached.”
2 | Standard procedure (87) | The executives are all located on floor 3
3 | Training in standard procedure (77) | The air con A46 & B2 does not work.
4 | Working AV equipment (52) | The heating in the 2 interview rooms is poor
Financial Validation |  |  | Total | Lessons Learned & Next Steps
| Actual savings $ |  | not required for YB projects | 1. | The data collection and presentation, as well as involving a wide range of stakeholders, really helped to get buy-in.
|  |  |  | 2. | The team will present at the global opEx meeting in October.
| Finance sign off |  |  | 3 | The next project for this team is to develop a group of personnel for greeting visitors at the reception area rather than hire contract staff.
www.LeanIreland.ie, +353 91 870708, info@LeanIreland.ie
Note on B2: use standard project numbering system (e.g. 2011-XX) and simple short name
Note on B8: State which strategic objective or programme to which this project best belongs OR does the project contribute to - safety - compliance - business growth - cost reduction - service quality improvement - product quality improvement
Note on B11: DEFINE PHASE ACTIVITIES 1. Define the problem in terms of impact on the customer & stakeholders 2. Select the area/process & open A3 (i.e. the project charter) in Excel 3. Form the team (stakeholders) 4. Elect a leader 5. Determine the objectives Objective format: Action verb + object of the action + from "current state" + to "future state" by "date" e.g Decrease average manufacturing lead time for product X from 10 days to 2 days by 31 Jaunary 2011" 6. Draft the project plan (Gantt chart) using DMAIC template (template exists in AtTask) 7. Train the team 8. Develop draft financial gains and get finance approval 9. Draft SIPOC and map the process TOOLS: A3 template, surveys & voice of the customer results, problem statement, goals, Gantt chart, Microsoft Project (large projects), SIPOC, process map
Note on E11: MEASURE PHASE ACTIVITIES 1. Walkthrough: team ‘discovers’ the project area by taking a guided tour and a walk through the current process 2. Collect relevant data on processes 3. Validate the measurement system 4. Select data representation charts & draw them TOOLS: check sheet, gauge R&R, run chart, bar chart, histogram, Pareto chart, box plot, PCA
Note on H11: ANALYSE PHASE ACTIVITIES 1. Root cause process problems 2. Identify areas for improvement 3. Prioritise issues 4. Identify and make ready all tools an equipment for change in advance of the of the event TOOLS: 5 whys, cause and effects analysis,PCA, data stratification, scatter diagrams, regression, Pareto charts, FMEA
Note on K11: IMPROVE PHASE ACTIVITIES 1. Draw up timetable of tasks and responsibilities for pilot trials and implementation 2. Convene team at the area, pilot & implement changes 3. Train personnel in new way of doing things 4. Standardise new processes, update procedures, implement visual management TOOLS: Project Gantt chart - tasks and timelines, detailed timetable of events, 5S, layout changes, standard work, SMED, TPM, visual workplace, error proofing, FMEA
Note on N11: CONTROL PHASE ACTIVITIES 1. Conduct post implementation review - snag list & action items 2. Use control charting to prove results and maintain discipline in th area 3. Confirm the financial gains 4. Present to senior management 5. Recognise and reward the team 6. Determine the next improvement activities for the team TOOLS: run chart, control chart, histogram, PCA, FMEA, costing guidlines & signoff
Note on B46: TOOLS: See "cost savings checklist" tab, this file See "Cost incurred" tab, this file
Note on F46: A separate sheet should be supplied with all the cost workings i.e. add a final tab for Cost analysis to this file. The traget for green belt level projects is $30K annualised savings, or better
Note on C49: Signature of finance cost accountant required

## Scope Is - Is Not sheet
Document: | Six Sigma A3 DMAIC template
Tab: | IS /IS NOT ANALYSIS
Source: | Lean Ireland
Contact: | Bernie Rushe, Bernie@LeanIreland.ie, +353 91 870708
Used to develop a problem statement and define the scope of a project.
Sample questions | IS (Observation): | IS NOT (Observation): | NOTES
What is the defect/problem?
What process/product/service?
Where in the process/product/service ?
Who is affected?
When does/did it happen?
How frequently does/did it happen?
Is there a pattern?
What is the impact on stakeholders & the customer?
How much is it costing?
Problem Statement (compiled from the IS column):
Project Scope (compiled from the IS and IS NOT columns):
| Includes | Excludes

## Goal Guidelines
Document: | Six Sigma A3 DMAIC template
Tab: | GUIDELINES FOR WRITING A CLEAR, RESULTS FOCUSED GOAL
Source: | Lean Ireland
Contact: | Bernie Rushe, Bernie@LeanIreland.ie, +353 91 870708
Sequence | Activity | Example
Start with | Action verb | Increase
add | object of the action | The right first time on application forms
add | from current state | from average 2.5 defects on each form received
add | to future state | to average 1 (one) defect on each form received
finish with destintion date | by date | by 31 October 2026
SMART Goals | Specific
Measurable
Achievable
Relevant
Time bound

## SIPOC template
Organisation:
| Process: | SIPOC CHART - xxx
Process owner:
Facilitator:
Date:
SUPPLIER | INPUT |  | PROCESS | OUTPUT | CUSTOMER

## Fishbone template
Quality Tools
Cause and Effect Diagram
| Description |  | Measurement | Materials | Method
This template illustrates a Cause and Effect Diagram, also called a Fishbone or Ishikawa Diagram. A detailed discussion of Cause and Effect Diagrams can be found at www.ASQ.org
Learn About C and E Diagrams
Instructions
| • | Enter the Problem Statement in box provided.
| • | Brainstorm the major categories of the problem. Generic headings are provided.
Problem Statement
| • | Write the categories of causes as branches from the main arrow.
Learn More
To learn more about other quality tools, visit the ASQ Learn About Quality web site.
Learn About Quality
|  |  | Environment | Manpower | Machine

## Dropdowns
INSERT ORGANISATION VALLUES/MISSION/OBJECTIVES HERE
VALUES
Customer satisfaction
Employees wellbeing
Innovation
One team
Integrity in everything we do